## Scope of Engagement

The objective of this engagement is to support GM Financials in ensuring the scalability, stability, and reliability of key digital applications through structured performance testing and quality assurance activities.

The scope of work includes the onboarding and testing of the following applications and services.

### Applications in Scope

- MyAccount (Consumer Web & Mobile)

- My Dealer App

- PayNow

- DPP

- CIAM/CPM

- Enterprise correspondence

- CCAS

### Scope of Work

Application Onboarding & Understanding

- Application walkthrough sessions

- Architecture and dependency mapping

- Identification of critical workflows and APIs

- Definition of performance and quality criteria

Test Design & Engineering

- Workload modeling across web, mobile, and/or APIs

- Identification of business-critical scenarios

- Test plan creation and coverage definition

Script Development & Engineering

Test scripts will be developed for:

- Load testing

- Stress testing

- Endurance testing

All scripts will include:

- Parameterization

- Correlation

- Assertions for validation

- Reusability across cycles

Test Execution & Validation

- Load and stress testing

- Endurance testing

- Controlled validation of system behavior under varying conditions

Analysis & Recommendations

- End-to-end system monitoring

- Bottleneck identification

- Root cause analysis & recommendations

Reporting & Governance

- Test execution summaries

- Performance and analysis reports

- Consolidated reporting for stakeholders

## High-Level Timeline

The program is expected to run over approximately six months, with activities structured in phased onboarding waves with approx target start date as 15th April

| Application | Phase | Purpose | M1 | M2 | M3 | M4 | M5 | M6 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| MyAccount - Web | Phase1 | App Walkthrough, Prod Traffic Analysis, Setup, Test Plan | 100% |  |  |  |  |  |
|  | Phase2a | Scripting, Scenario Design, Test data, Environment |  | 100% |  |  |  |  |
|  | Phase2b | Test Runs, Monitoring, Analysis |  | 50% | 50% |  |  |  |
|  | Phase3 | Load Test After Tuning, Baseline comparison |  |  | 100% |  |  |  |
|  | Phase4 | Reports, Handover |  |  |  | 100% |  |  |
| MyAccount - Mobile | Phase1 | App Walkthrough, Prod Traffic Analysis, Setup, Test Plan | 100% |  |  |  |  |  |
|  | Phase2a | Scripting, Scenario Design, Test data, Environment |  | 100% |  |  |  |  |
|  | Phase2b | Test Runs, Monitoring, Analysis |  | 50% | 50% |  |  |  |
|  | Phase3 | Load Test After Tuning, baseline comparison |  |  | 100% |  |  |  |
|  | Phase4 | Reports, Handover |  |  |  | 100% |  |  |
| MyDealership - API | Phase1 | App Walkthrough, Prod Traffic Analysis, Setup, Test Plan | 100% |  |  |  |  |  |
|  | Phase2a | Scripting, Scenario Design, Test data, Environment |  | 100% |  |  |  |  |
|  | Phase2b | Test Runs, Monitoring, Analysis |  | 50% | 50% |  |  |  |
|  | Phase3 | Load Test After Tuning, baseline comparison |  |  | 100% |  |  |  |
|  | Phase4 | Reports, Handover |  |  |  | 100% |  |  |
| MyDealership - Mobile | Phase1 | App Walkthrough, Prod Traffic Analysis, Setup, Test Plan | 100% |  |  |  |  |  |
|  | Phase2a | Scripting, Scenario Design, Test data, Environment |  | 100% |  |  |  |  |
|  | Phase2b | Test Runs, Monitoring, Analysis |  | 50% | 50% |  |  |  |
|  | Phase3 | Load Test After Tuning, baseline comparison |  |  | 100% |  |  |  |
|  | Phase4 | Reports, Handover |  |  |  | 100% |  |  |
| PayNow - Web | Phase1 | App Walkthrough, Prod Traffic Analysis, Setup, Test Plan | 100% |  |  |  |  |  |
|  | Phase2a | Scripting, Scenario Design, Test data, Environment |  |  |  | 100% |  |  |
|  | Phase2b | Test Runs, Monitoring, Analysis |  |  |  | 50% | 50% |  |
|  | Phase3 | Load Test After Tuning, baseline comparison |  |  |  |  | 100% |  |
|  | Phase4 | Reports, Handover |  |  |  |  |  | 100% |
| DPP - API | Phase1 | App Walkthrough, Prod Traffic Analysis, Setup, Test Plan | 100% |  |  |  |  |  |
|  | Phase2a | Scripting, Scenario Design, Test data, Environment |  |  |  | 100% |  |  |
|  | Phase2b | Test Runs, Monitoring, Analysis |  |  |  | 50% | 50% |  |
|  | Phase3 | Load Test After Tuning, baseline comparison |  |  |  |  | 100% |  |
|  | Phase4 | Reports, Handover |  |  |  |  |  | 100% |
| CIAM/CPM - API | Phase1 | App Walkthrough, Prod Traffic Analysis, Setup, Test Plan | 100% |  |  |  |  |  |
|  | Phase2a | Scripting, Scenario Design, Test data, Environment |  |  |  | 100% |  |  |
|  | Phase2b | Test Runs, Monitoring, Analysis |  |  |  | 50% | 50% |  |
|  | Phase3 | Load Test After Tuning, baseline comparison |  |  |  |  | 100% |  |
|  | Phase4 | Reports, Handover |  |  |  |  |  | 100% |
| Enterprise Correspondence | Phase1 | App Walkthrough, Prod Traffic Analysis, Setup, Test Plan | 100% |  |  |  |  |  |
|  | Phase2a | Scripting, Scenario Design, Test data, Environment |  |  |  |  | 100% |  |
|  | Phase2b | Test Runs, Monitoring, Analysis |  |  |  |  | 50% | 50% |
|  | Phase3 | Load Test After Tuning, baseline comparison |  |  |  |  |  | 100% |
|  | Phase4 | Reports, Handover |  |  |  |  |  | 100% |
| CCAS | Phase1 | App Walkthrough, Prod Traffic Analysis, Setup, Test Plan | 100% |  |  |  |  |  |
|  | Phase2a | Scripting, Scenario Design, Test data, Environment |  |  |  |  | 100% |  |
|  | Phase2b | Test Runs, Monitoring, Analysis |  |  |  |  | 50% | 50% |
|  | Phase3 | Load Test After Tuning, baseline comparison |  |  |  |  |  | 100% |
|  | Phase4 | Reports, Handover |  |  |  |  |  | 100% |

## Execution Model

The engagement will be delivered by a dedicated team consisting of Cavisson engineers to distribute the above mentioned workload over a period of ~6 months, structured as follows:

Performance Engineers
Responsible for:

- Test design and workload modeling

- Script development

- Test execution and monitoring

- Performance analysis

Test Manager / Program Lead

Responsible for:

- Overall program governance

- Stakeholder coordination

- Test strategy oversight

- Reporting and status updates

The team will work closely with the client’s development and QA teams to ensure alignment with application releases and testing schedules.

## Deliverables & Reporting Framework

The engagement will produce the following deliverables.

Test Strategy & Planning

- Performance Test Plan

- Workload Model Documentation

Test Execution

- Test Scripts and Scenarios

- Execution Results

Analysis

- Performance Analysis Report

- Bottleneck identification & recommendation

Final Reporting

- Consolidated Performance Testing Report

- Production Readiness Summary

Governance Reporting

- Monthly status updates

- Event driven reporting

GM Financials Point of Contacts

Primary PoC: Munish Kumar

Secondary PoC: Naresh Shroff

Additionally, respective application SMEs

### Note: The scope and timeline presented above are indicative estimates based on the current understanding of application readiness and dependencies. Actual timelines may vary depending on environment readiness, access provisioning, and integration dependencies.